## Proposal
PROJECT | WHAT ARE THE CRIME HOTSPOTS IN METRO CHICAGO?
DATA ANALYTICS TEAM | Edwin Banks,
DESCRIPTION | The scope of our research project is to analyze and present data regarding group A (violent) crimes to help the class come to a conclusion on the safest areas of Chicago.
RESEARCH QUESTION TO ANSWER | Does climate factor in to crime rates? What is the peak time of year for crime? Are the hotspots for crime consistent throughout the year?
DATA SETS TO BE USED | Kaggle-Chicago Crime, Data.gov, Bureau of Justice
ROUGH BREAKDOWN OF TASKS | Data Mining/Cleanup, Coding

## Plan
TASK |  | NAME | DESCRIPTION | FROM | TO | STATUS | TASK DEPENDENCY | DATE COMPLETED | PRIMARY OWNERS | ADDITIONAL OWNERS / COMMENTS | ROAD BLOCKS / CHALLENGES / DEPENDENCIES
1 |  | PREPARATIONS | [7 empty] | Onlly optional tasks remain open
| a | Proposal - Initial Cut |  | 2019-07-22 | 2019-07-22 | submitted |  | 2019-07-22 | Team | Jonathan - published first cut to Dr A
| b | Data Source - Initial Selections | Identify set of potential data sources | 2019-07-22 | 2019-07-22 | submitted |  | 2019-07-22 | Team | Nathan, Jonathan, James, Edwin, Scott, Lina
| c | Team Assignments |  | 2019-07-22 | 2019-07-22 | assigned |  | 2019-07-22 | Team
| d | Project Plan |  | 2019-07-22 | 2019-07-22 | done |  | 2019-07-22 | Team | Ray
| e | GIT setup |  | 2019-07-23 | 2019-07-23 | done |  |  | Nathan
| f | Proposal - Final Cut |  | 2019-07-23 | 2019-07-27 |  |  |  | Team | Jonathan - working on potential scope changes
| g | Data Sources - Final scope |  | 2019-07-23 | 2019-07-27 |  |  |  | Nathan, Team | James - chasing after walkscore file and CPD Edwin - charlotte file Ray - household inc file
2 |  | DATA MINING
| a | Data Sources | Final list of candidate data sources across same dimensions (period, scope, etc) | 2019-07-22 | 2019-07-23 | done |  |  | Nathan, Team | Edwin, James, Jonathan, Scott Initial data sources finalized on 7/23.
| b | Data Pre-Validation, Extracts and Cleanup | Cross check data sources and identify challenges, constraints, road blocks | 2019-07-23 | 2019-07-24 | done | 2.a |  | Basanta, Amrita, Jonathan, Ray | Jonathan - weather file merge / scrub & calc Ray - crime file merge / scrub & 2018 Pivot Data Analysis
| c | Final Validations | Must complete before comparing results of coding (3.b and 4.b) | 2019-07-25 | 2019-07-26 | done | 2.b |  | Basanta, Amrita | Team Amrita confrmed back to team
3 |  | TEAM 1 | Code for data extracts and analytics, and compare results / conclusions with TEAM 2 |  |  |  | 2.b |  | Scott, Lina | Team
| a | BUILD |  | 2019-07-24 | 2019-07-29 | done
| b | COMPARE and ANALYZE | Code will be owned by PRIMARY OWNERS. Code contributions from TEAM can be integrated, appended upon agreement. | 2019-07-27 | 2019-07-29 | done | 2.c ¦ 3.a
4 |  | TEAM 2 | Code for data extracts and analytics, and compare results / conclusions with TEAM 1 |  |  |  | 2.b |  | Nathan, Ray | Team
| a | BUILD |  | 2019-07-24 | 2019-07-29 | done
| b | COMPARE and ANALYZE | Code will be owned by PRIMARY OWNERS. Code contributions from TEAM can be integrated, appended upon agreement. | 2019-07-27 | 2019-07-29 | done | 2.c ¦ 4.a
5 |  | TEAM 3 | Optional: Code for additional granularity, and integrate into work done by TEAM 1 & TEAM 2 | [5 empty] | Edwin | Team
| a | BUILD |  | 2019-07-24 | 2019-07-31 | done
| b | COMPARE, ANALYZE and INTEGRATE |  | 2019-07-27 | 2019-07-31 | done
6 |  | VISUALIZERS | Evaluate relevant visualizations in scope. Heat map is suggested by Scott so far. | [5 empty] | Scott (?) Nathan (?) Line (?) James (?) | Team
| a | BUILD |  | 2019-07-26 | 2019-07-28 | done | 3.a ¦ 4.a
| b | INTEGRATE into final code |  |  | 2019-07-29 | done | 6.a
7 |  | PRESENTATION
| a | Craft presentation format & required materials |  | 2019-07-22 | 2019-07-31 | done |  |  | James | Team
| b | Finalize presentation & Materials |  | 2019-07-28 | 2019-08-01 | done | 3.b ¦ 4.b 5.b ¦ 6.b
| c | Presentation Mock |  | 2019-08-02 | 2019-08-03 | in progress | 7.b
| d | Filler
| e | Presentation |  |  | 2019-08-03
| f | Team Celebrations :) |  |  | 2019-08-03
critical path

## Data Analysts
|  |  | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03
NAME | Email | NOTES | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
James Rogers
Amritagurung
Basanta
Edwin Banks
Jonathan Richards
Lina Kalala
Nathan Deering | nrdeering@gmail.com
Ray Marquez | ray.marquez.edu@gmail.com | Not available on Saturday 27th (after class) to catch a flight. Will be back on 29th (Monday) for the class | 2019-07-27: out after 4pm; 2019-07-28: out; 2019-07-29: remote; 2019-07-30: calls only
Scott Caldwell |  | On vacation on Wednesday 24th?? | 2019-07-24: out

## Presentation
F.B.I Analytics Team
We would be visiting Charlotte/Portland/Chicago to make a presentation/debrief to city officials, delivering critical crime data that our lab has come up with.
The class would be the City Council, Dr. A = Mayor.
The 'why' of our visit could be the path to narrow our scope.
I think it would be a cool and useful prop. We could even look 'governmental' in our uniform for the evening to play it out (Party City badges on me).
INTRO | BACKGROUND |  |  | Chicago? Why? Weather? Wealth?
PROPOSAL
PURPOSE
ANALYST
CORE | DATA ANALYTICS |  |  |  | VISUALIZATION TOOLS
Crime
Weather
Wealth
CONCLUSIONS
STORY OF DATA (RECAP)
RECOMMENDATIONS
VALUE ADD RECAP
Q&A

## Sources
|  | DATA SOURCES | ANALYST | HIGHLIGHTS / CONCLUSIONS | LINK
2019-07-22 | 1 | MEDIUM APIs | Nathan |  | https://medium.com/@benjamin_libor/a-curated-collection-of-over-150-apis-to-build-great-products-fdcfa0f361bc
| 2 | Charlotte NC Open Data Portal | Nathan |  | http://data.charlottenc.gov/
| 3 | Charlotte NC Census Poverty Tracts | Nathan | Census data has 2011 - 2015. Kind of stale | http://data.charlottenc.gov/datasets/census-poverty-tracts
| 4 | Defintions of Crime | Ray | Can be used to help with defintions of a "crime" | https://www.fbi.gov/news/stories/2017-crime-statistics-released-092418
| 5 | Bureau of Justice Statistics - All Data | Edwin |  | https://www.bjs.gov/index.cfm?ty=dca
| 6 | Kaggle - Chicago Crime | Scott |  | https://www.kaggle.com/chicago/chicago-crime
| 7 | Kaggle - Recorded Crime at Police level | Ray |  | https://www.kaggle.com/r3w0p4/recorded-crime-data-at-police-force-area-level
| 8 | Chicago Crime | James | Posted attachment - attached / posted in Git Has data from 2012-2017
| 9 | APIs for crimes etc | James |  | https://linc.osbm.nc.gov/explore/?sort=modified
| 10 | NCSBI | James | Called & left messages requesting raw data 919.662.4500 | https://www.ncsbi.gov/Services/SBI-Statistics
| 11 | Charlotte Police | James | Called & left messages requesting raw data Crime Analysis Division ¦ 601 E.Trade Street ¦ 704.353.0780 Division Supervisor: Monica Nguyen
| 12 | Crimes 2017 & 2018 | Nathan | Attached in Google drive. Each set has 52k+ crimes -- looking robust | https://drive.google.com/drive/folders/1utL_DAP-IjcoWxNu9am9lsq7IWbz7088?usp=sharing